## Full Report
Decentralized Capital Budget Programme - 2017 | [44 empty] | Annexure No.2
Distict wise Physical and Financial Progress as of 31st December 2017
Division: WELLAWAYA
No. | Division | No. of Eligible GN Divisions | Projects | [14 empty] | Total Estimated Cost (Rs.Mn) |  | Allocation | [14 empty] | ** Physical Progress (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  |  | No. of Projects Approved |  |  | Total categorized by Sectors * | [13 empty] | Allocation Made (Rs.Mn) |  |  | Total Allocation Categorized by Sectors * | [11 empty] | A | B |  |  |  | C | D | E | F | G
|  |  | Construction | Goods / Services Purchase | Total | WS | EL | RA | EI | RW | CD | MI | SW | SS | CP | LD | RE | With VAT | Without VAT | Construction | Goods / Services Purchase | Total | WS | EL | RA | EI | RW | CD | MI | SW | SS | CP | LD | RE |  | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4)
1 | 01 Development of 450m of Diwlgahakanaththa road of Sudupanawela GN division and From Udawela temple to Rambukkatiya warunagama Road | 405 | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 298297.78 | 259389.38 | 300000 | 0 | 300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 243813.76
2 | Development of Gampanguwa Weeraththagalayaya By road | 672 | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 99350.89 | 86392.08 | 100000 | 0 | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  |  | 1 | 97200 |  |  | 159622.3
3 | Motor gradering and Gravelling the road warunagama Batahelayaya road | 540 | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 299525.55 | 260457 | 300000 | 0 | 300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 244896 |  |  | 4713135.52
4 | Gravelling the 3rd river road of Debaraara Gamunupura | 297 | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 449999.6 | 391304 | 450000 | 0 | 450000 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 358001 |  |  | 1123517.33
5 | Renovation of the by road of upper part of Dodammandiya village | 355 | 1 | 0 | 1 | 0 |  | 1 | [10 empty] | 0 | 300000 | 0 | 300000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 258886.39 |  |  | 284025 | 6280300.15
6 | Development of two Cemeterie of Galbokka GN Division | 853 | 1 | 0 | 1 | 0 | [7 empty] | 1 | [5 empty] | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 1 | 42500 |  |  | 24381
7 | Completion of the building of Dimbulamuraya DIVI SAVI Welfare and Funaral Society | 1105 | 1 | 0 | 1 | 0 |  |  |  |  | 1 | [6 empty] | 193985.16 | 168682.74 | 194000 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 | 1 | 159622.3 |  |  | 24508.6
8 | Development of Paragasmankada Maragahawatta By Road |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 193456.47 | 168223.02 | 194000 | 0 | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 152368.9 |  |  | 24427.53 | 73317.13
9 | Renovation of the access road to Anjaligama Farmer Village |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 193300.4 | 168087.3 | 194000 | 0 | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 1 | 162850.2 |  |  |  | 6206983.02
10 | Renovation of Road to Anjaligama Hanadapanagala Irrigation cannel road |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 193878.81 | 168590.27 | 194000 | 0 | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 1 | 163390.7
11 | Renovation of Weerasekaragama Dewala Road |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 193404.16 | 168177.53 | 194000 | 0 | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 1 | 193839.35
12 | Renovation of the Roof of Thelulla colony GAMUNU Funeral Society Hall |  | 1 | 0 | 1 | 0 |  |  |  |  | 1 | [6 empty] | 104865.18 | 120594.96 | 121250 | 0 | 121250 | 0 | 0 |  | 0 | 0 | 121250 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 1 | 104865.18
13 | Development of the road between Wandinahelayaya cannel and carpet road |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 193038.08 | 167859.2 | 194000 | 0 | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 1 | 162560
14 | Construction of Pavilion of Mo/ Ethiliwewa M.V |  | 1 | 0 | 1 | 0 |  |  |  |  | 1 | [6 empty] | 199994.3 | 173908.66 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 165099.5
15 | Motor Gradering the 4th road of Weherayaya Colony GN Division |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 199996.5 | 173910 | 200000 | 0 | 200000 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 144359.75
16 | Construction a Side Wall near the road of Weerasekaragama Malewana Society Hall |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 192224.59 | 167151.82 | 194000 | 0 | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 1 | 158001.5
17 | Extension of Water line to Wellawaya Haputale road Malwattawela village |  | 1 | 0 | 1 | 1 | [11 empty] | 199994.96 | 173908.66 | 200000 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 1 | 199282.03
18 | Completion of Rural Elder center's building of warunagama GN division | 569 | 1 | 0 | 1 | 0 |  |  |  |  | 1 | [6 empty] | 199005.04 | 167830.47 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 166905
19 | Construction of Storage room for yalabowa funeral society building | 391 | 1 | 0 | 1 | 0 |  |  |  |  | 1 | [6 empty] | 193801.37 | 161501.14 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 | 1 | 147682.43
20 | Development of perakatiya Road | 762 | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 193852.57 | 168567.46 | 194000 | 0 | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 159727.47
21 | Giving meterials to maintarnance of Anapallama Water project | 1147 | 1 |  | 1 | 1 | [12 empty] | 0 | 194000 |  | 194000 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 193815
22 | Construction of Multipupose building | 573 | 1 | 0 | 1 | 0 |  |  |  |  | 1 | [6 empty] | 193996.24 | 167442.39 | 194000 |  | 194000 | 0 | 0 | 0 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 161373.85
23 | Construction of a new office room to malwaththawala primary School | 95 | 1 | 0 | 1 | 0 | [6 empty] | 1 |  |  |  |  | 197816.27 | 164846.89 | 194000 |  | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 | 1 | 147704.17
24 | Fixing a Door to Abode of Thelulla Colony Sri Bhodhirukkarama Temple | 1598 | 1 | 0 | 1 | 0 |  |  |  |  | 1 | [6 empty] | 43207.34 | 37571.6 | 43650 |  | 43650 | 0 | 0 | 0 | 0 | 0 | 43650 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 | 1 | 35200
25 | Giving meterials to construct for Sri Dharmarama Dhamma school building | 153 | 1 |  | 1 | [5 empty] | 1 | [8 empty] | 97000 |  | 97000 |  | 0 | 0 | 0 | 0 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 1 | 95550
26 | Fixing a gate to Anandapura Kakulu Pre school |  | 1 | 0 | 1 | 0 | [9 empty] | 1 |  | 29095 | 25300 | 29100 |  | 29100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29100 | 0 |  | 0 |  |  |  | 0 | 0 |  | 0 | 1 | 24528.64
27 | Gravelling necessary places from Dhodhol Shop to Maharagama bus road |  | 1 | 0 | 1 | 0 |  | 1 | [9 empty] | 193999.25 | 168695 | 194000 |  | 194000 | 0 | 0 | 194000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 159978.9
28 | Completion of the Buddha shrine of Weherayaya Sri Gangarama Temple |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 1 | 199985
29 | Giving Materials to construction of alms-hall of Uva karandagolla Rakkiththakanda temple |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 29700
30 | Giving Desks and chairs to Yalabowa Mohideen Muslim church's Dhamma School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  | 1 | 29675
31 | Giving Materials to Kotaweheragala Ruaral Elder Society building |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 1 | 30000
32 | Giving Megaphone to Batahelayaya Funeral Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 30000
33 | Giving Materials to Consruct Pahalawarunagama SANDARAS Funeral Socirty Building |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 | 1 | 25320
34 | Giving a plastic water tank to weherayaya dematathara SAMAGI Funeral Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 11500 | 11500 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 1 | 10245
35 | Giving Plastic chairs to Yalabowa Methodiyas Council Welfare Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 19575
36 | Giving Materials to develop the Buddha Shrine of Andawelayaya Kinkini Temple |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 49980
37 | Giving Materials to 32C, Savijaya Mawatha , Ella road Pre School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 1 | 49950
38 | Giving Materials to norms-hall of Perakatiya Gangarama Temple |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 |  | 0 | [6 empty] | 0 | 1 | 74970
39 | Giving Materials to cunstruct Valigamvehera Temple |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  |  | 1 | 49500
40 | Giving Materials to develop SADDHATHISSA ARANNYA SENASANAYA |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 99910
41 | Giving Asbestos sheets to Thelulla Bodhirajarama Temple's Monastery |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 68800 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 48720
42 | Giving WES ANDUM SETS to Ella Road BATHIYA LALITHA KALAYATHANAYA |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 1 | 25000
43 | Giving Materials o Ulahitithanna Funeral Society and Welfare Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 1 | 24845
44 | Giving a tin hut to SUNEETHA Funeral Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  |  | 1 | 39500
45 | Giving Materials to Randeniya 06th Mile post SAMAGIWARDHANA Funeral Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 | 1 | 23790
46 | Giving Materials to Kurugama Hunukatiya Gnanapradeepa Funeral Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1 | 24975
47 | Giving Materials to Kithulkote SAMADHI Funeral Society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 24300
48 | Giving Materials to Tile Balaharuwa Temple's Monastery |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 1 | 69200
49 | Giving a AMP set to Mo/Mallaththawela School |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 1 | 25000
50 | Giving steel cupboards to Sri Chandabimbarama Temple's Dhamma School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 10000
51 | Giving steel cupboards to Thelulla Bodhirajagama Temple's Dhamma School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  | 1 | 10000
52 | Giving steel cupboards to Malwaththawala Temple's Dhamma School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 10000
53 | Giving steel cupboards to Buduruwagala Temple's Dhamma School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 10000
54 | Giving steel cupboards to Weherayaya Colony 3 piyawara Temple's Dhamma School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 1 | 10000
55 | Construction of the Building of Nugayaya Sri Gnavimalarama Temple |  | 0 | 1 | 1 | 0 | [7 empty] | 1 |  |  |  |  | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 174485
56 | Giving Sport Instruments to Wellawaya Sport Club |  | 0 | 1 | 1 | 0 | [6 empty] | 1 | [5 empty] | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  | 1 | 19500
57 | Giving Materials to improve skill promoting activities of children in Registered Early Childhood Development centers in wellawaya Division |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 |  | 0 |  |  |  | 0 | 0 |  |  | 1 | 349763.7
58 | Giving a Book set to Thelulla colony Library (39th Mile post) |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | [9 empty] | 1 | 18135 |  | 4304002.02 | Project | 26 | 26 | 0 | 100
59 | Giving a steel Pyramid to Warunagama Minimuthu Pre School |  | 0 | 1 | 1 | 0 | [9 empty] | 1 |  |  | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 1 | 20900 |  | 1805798.7 | Goods | 38 | 38 | 0 | 100
60 | Giving 10feet Asbestos sheets to Handapanagala Youth Arunalau Funeral Society |  | 0 | 1 | 1 | 0 | [6 empty] | 1 | [5 empty] | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 39800 |  | 6109800.72 |  | 64 | 64 | 0 | 100
61 | Giving Chairs to Ethiliwewa Registered Arunashantha Funeral Society |  | 0 | 1 | 1 | 0 | [6 empty] | 1 | [5 empty] | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 1 | 19575 |  | 87.3515
62 | Giving a mega phone to Government service pensioners welfare society |  | 0 | 1 | 1 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  | 1 | 45000
63 | Giving water connection to Kudaoya Vishaka Pre chilhood center |  | 0 | 1 | 1 | 1 | [12 empty] | 25562.5 | 0 | 22000 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 22000
64 | Development of Cemeterie of Galbokka GN Division |  | 1 |  | 1 | [5 empty] | 1 | [8 empty] | 50000 |  | 50000 |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 42500
District Total |  | 9515 | 28 | 36 | 64 | 3 | 0 | 14 | 0 | 0 | 22 | 0 | 4 | 10 | 0 | 11 | 0 | 4450085.51 | 3972754.07 | 5169000 | 1825500 | 6994500 | 416000 | 0 | 3202000 | 0 | 0 | 1666400 | 0 | 279000 | 875000 | 0 | 556100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 6109800.72 | 0
.
| * Projects should be categorized for following sectors | [22 empty] | ** Physical progress | [19 empty] | 64
| WS- Rural Water Supply | [5 empty] | SS- Social Services | [10 empty] | 64 |  | 6994500 |  |  |  | A - Estimates are being / to be prepared
| EL- Rural Electricity | [5 empty] | CP- Community Protection | [12 empty] | 6994500 |  |  |  | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received , B-4= Contract Awarded
| RA- Rural Access | [5 empty] | LD - Livelihood Development | [16 empty] | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
| EI - Economic Infrastructure | [5 empty] | RE - Rural Economy | [12 empty] | 884699.28 |  |  |  | C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
| RW- Rural Welffare | [22 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
| CD- Community Development | [22 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
| MI- Minor Irrigation | [19 empty] | 0 |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
| SW- Social Welfare | [22 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
28