## Livelihood
Rural Infrastructure Development Programme (LIVELIHOOD DEVELOPMENT) Division vise Physical and Financial Progress as at 27th of December 2017
Wellawaya Divisional Secretariat
No | Name of Project | GN Division | Projects | [8 empty] | Total Estimated Cost |  | Allocation | [8 empty] | Physical Progress ** (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No of Beneficiaries
|  |  | No. of Project Approved |  |  | Total categorized by sectors* | [7 empty] | Allocation Made (Rs.Mn) |  |  | Total Allocation categorized by sectors
|  |  | Construction | Purchasing Goods / Services | Total | SF | RE | MI | WS | OI | LCD | With VAT | without VAT | Construction | Purchasing Goods / Services | Total | SF | RE | MI | WS | OI | LCD | A | B |  |  |  | C | D | E | F | G
[16 empty] | Total Allocation categorized by sectors B: B1 - Estimates Approved & Bid Document Prepared | B2 - Quotation/Bid called | B3 - Quotation / Bid Received | B4 - Cotract Awarded
1 | LIVELIHOOD DEVELOPMENT | Kurugama | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 11 | 0 | 84250 | 15
2 | LIVELIHOOD DEVELOPMENT | Siyambalagunaya | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 10 | 0 | 94160 | 15
3 | LIVELIHOOD DEVELOPMENT | Galbokka | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 13 | 0 | 111155 | 15
4 | LIVELIHOOD DEVELOPMENT | Wellawaya | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 132860 | 15
5 | LIVELIHOOD DEVELOPMENT | Yalabowa | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 13 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 0 | 83473 | 13
6 | LIVELIHOOD DEVELOPMENT | Anapallama | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 14 | 0 | 137200 | 15
7 | LIVELIHOOD DEVELOPMENT | Pubuduwewa | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 28 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 146160 | 28
8 | LIVELIHOOD DEVELOPMENT | Neluwagala | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 28 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 27 | 0 | 140940 | 28
9 | LIVELIHOOD DEVELOPMENT | Buduruwagala | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 18 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 12 | 0 | 89530 | 18
10 | LIVELIHOOD DEVELOPMENT | Siripuragama | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 22 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 21 | 0 | 141750 | 22
11 | LIVELIHOOD DEVELOPMENT | Weherayaya | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 24 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 146880 | 24
12 | LIVELIHOOD DEVELOPMENT | Mahaaragama | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 26 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 145080 | 26
13 | LIVELIHOOD DEVELOPMENT | Thelulla Colony | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 14 | 0 | 104744 | 15
14 | LIVELIHOOD DEVELOPMENT | Debaraara | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 14 | 0 | 126350 | 15
15 | LIVELIHOOD DEVELOPMENT | Kithulkote | 0 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 29 |  | 148500 | 0 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 148500 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 28 | 0 | 146695 | 29
| Total |  | 0 | 293 | 293 | 0 | 0 | 0 | 0 | 0 | 293 |  | 2227500 | 0 | 2227500 | 2227500 | 0 | 0 | 0 | 0 | 0 | 2227500 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 269 | 0 | 1831227 | 293
prepared by - checked by - approved by -

## Infrastructure Development
Rural Infrastructure Development Programme Division vise Physical and Financial Progress as at 31st of December 2017
Wellawaya Divisional Secretariat
No | Name of Project | GN Division | Projects | [8 empty] | Total Estimated Cost |  | Allocation | [8 empty] | Physical Progress ** (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No of Beneficiaries
|  |  | No. of Project Approved |  |  | Total categorized by sectors* | [7 empty] | Allocation Made (Rs.Mn) |  |  | Total Allocation categorized by sectors
|  |  | Construction | Purchasing Goods / Services | Total | SF | RE | MI | WS | OI | LCD | With VAT | without VAT | Construction | Purchasing Goods / Services | Total | SF | RE | MI | WS | OI | LCD | A | B |  |  |  | C | D | E | F | G
[16 empty] | Total Allocation categorized by sectors B: B1 - Estimates Approved & Bid Document Prepared | B2 - Quotation/Bid called | B3 - Quotation / Bid Received | B4 - Cotract Awarded
1 | Concreating Small Village road of 7th mile post | Kurugama | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346500 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 344820.86 | 25
2 | Development of Yodhaara Road | Randeniya | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 494816.84 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 488809.59 | 150
3 | Concreating the Polgaspitiya middle road from Mr Saman's house to forward | Siyambalagunaya | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 344012.11 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 324991.16 | 40
4 | Developing the road near to Mr Gunasena's house of Rambukkatiya upper part | Sudupanawela | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 493361.06 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 493328.26 | 412
5 | Development of Heenapahuwa Rural water project | Kotikanbokka | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 0 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 495000 | 80
6 | Concreating the road to Illukkatiya village | Galbokka | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346441.6 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346423.89 | 30
7 | Renovation of last part of Prathapasinghe Mawatha (from community hall to radhapola bridge) | Dimbulamure | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 494733.04 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 486526.01 | 120
8 | Concreating Nikapitiya Middle Road | Wellawaya | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 344792.55 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 337043.65 | 50
9 | Developing upper part of Sellaba 2nd road | Yalabowa | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 345933.58 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 345693.57 | 50
10 | Renovation of the road near to Mr A.A Amarasekara's house | Nugayaya | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 494374.9 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 426156.3 | 15
11 | Renovation of the road from Mr Bandara's shop to cemetory of Warunagama model village | Warunagama | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 494332.58 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 488332.58 | 300
12 | Developing the road from Mr jayantha's shop to Pethiyanara | Anapallama | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 344745.3 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 344745.3 | 40
13 | Developing the Olugaa road by laying Gravel | Pubuduwewa | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346500 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346500 | 100
14 | Gravelling the road from Mr A.M Jayasinghe's house to Mr K.D Guneris's house | Neluwagala | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346002 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 345113.75 | 35
15 | Developing the 2nd by road of Samagi Mawatha | Buduruwagala | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 344752.27 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 336420.81 | 20
16 | Developing North Mahathanna (Beginning from SANASA Junction) road up to karuwala kanda | Andawelayaya | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 493500 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 493500 | 200
17 | Concreating the stone rock between dematathara road and diggalyaya road | Siripuragama | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346500 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 338610.86 | 200
18 | Concrating the road near to the 3/200 house of Nuge road | Weherayaya Colony | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 491394.44 | 250
19 | Developing the road near to Weherayaya scholl Gate | Weherayaya | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346500 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 343123.72 | 200
20 | Renovation of Farm road | Randenigodayaya | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 495000 | 150
21 | Renovation of the road from Kirimatiwala junction to Hewangala road with a causeway | Handapanagala | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 495000 | 200
22 | Concreating the school road from Mahaara causeway to School | Mahaaragama | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346500 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 340440.58 | 100
23 | Gravelling the road with construction of a couseway to the road to right side from bogaha junction of R07 upper road | Thelulla Colony | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346500 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 346500 | 75
24 | Renovation of Adhikari road | Ethiliwewa | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 495000 | 200
25 | Developing Thelullagalayaya Road | Thelulla | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 495000 | 50
26 | Renovation of Sooriyagodana Temple road | Balaharuwa | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 495000 | 50
27 | Renovation of the road from Samagipura junction to New Balaharuwa road | Debaraara | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 346500 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 342375 | 100
28 | Gravelling the Nidahas mawatha from Main road to Shakthi mawatha | Kithulkote | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 345922.25 | 346500 | 0 | 346500 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 342307.25 | 75
29 | Concreating the Main cannel of Waliara tank | Uva Kudaoya | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 495000 | 495000 | 0 | 495000 | 0 | 0 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 429020.82 | 50
30 | Livelihood Development |  | 0 | 293 | 293 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2227500 | 0 | 2227500 | 2227500 | 0 | 0 | 0 | 0 | 0 | 2227500 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 269 | 1928951 | 293
| Total |  | 29 | 293 | 322 | 0 | 27 | 1 | 1 | 0 | 0 |  | 14340720.08 | 12127500 | 2227500 | 14355000 | 0 | 11137500 | 495000 | 495000 | 0 | 2227500 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 298 | 13821129.4 | 3660

## Sheet2
MI | Minor Irrigation (Constructions and renovations of canals, anicuts, ponds, and agro wells under the minor irrigation projects for agricultural activities)
CBWS | Community Based Water Supply (community based water supply projects both rehabilitation and new construction to improve the drinking water and common bathing)
SSE | Small Scale Electrification (Small scale electriciry projects)
RA | Rural Access (Rural Roads, foorsteps rural bridges, culverts and foot bridges (Rehabilitation / New constructions)
OIP | Other Infrastructure Projects Which Leads to Rural Livelihood Development
DG | Direct Grant

## Sheet3
A |  | Estimates are being / to be prepared
B | Constructions | Estimate prepared and approved, bid documents prepared, quataion called, tender awarded
| other | Identified intitutions / cbo's to provide goods / instruments, obtain required list of good's , Estimate prepared
C | Constructions | Start construction work and 40% completed
| other | Placed orders for goods
D | Constructions | 60% Completed
| other | Received goods / Instruments as per the order
E | Constructions | 80% completed
| other | Received goods / Instruments as per the order
F | Constructions | 99% completed
| other | Completed list of goods an beneficiaries
G | Constructions | 100% completed
| other | Issued goods and instruments to identified intitutions / CBOs