## Infrastrucrure Development
Rural Infrastructure Development Special Programme - 2017
Physical and Financial Progress As At 31st of December 2017
Divisional Secretariat Division Name: Wellawaya
Divisional Secretariat Division Number: 1242
SN | Name of Project | G.N Division |  | Sector | Type of Project(construction /Good & Services) | Total Estimate Cost(Rs.) |  | Allocation(Rs.) | Expenditure (Rs.) | Unit of Measure | Physical Progress | [9 empty] | No of Beneficiaries | Remarks
|  | Name | Number |  |  | With VAT | Without VAT |  |  |  | A | B |  |  |  | C | D | E | F | G
[12 empty] | B1 | B2 | B3 | B4
1 | Gravelling 1st step of The Road via warunagama lindara to Block 03 | Warunagama | 12565 |  | Construction |  | 1478398.95 | 1485000 | 1478398.95 | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 750
2 | Gravelling 2nd step of The Road via warunagama lindara to Block 03 | Warunagama | 12565 |  | Construction |  | 1479523.95 | 1485000 | 1478398.95 | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 750
3 | Gravelling the Weerasekaragama Yaya Road | Warunagama | 12565 |  | Construction |  | 1426214.25 | 1485000 | 1417289.16 | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 400
| Total | [5 empty] | 4384137.15 | 4455000 | 4374087.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1900
| prepared by - |  |  |  | checked by - | [9 empty] | approved by -

## Sheet2
Description for rating | Rates | Percentagr range
Estimate is being / to be prepared and initial works started | A | (0-5)%
B1 - Estimates Approved / Bid documents prepared | B1 | (6-25)%
B2 - Bid / Quatation called | B2
B3 - Bid / Quatation Received | B3
B4 - Contract awarded (25% completed) | B4
Other: Identified Institutions/CBO's to Provide Goods/Instruments obtailn required list of goods, Estimate prepared | B
Constructions: Strarted Construction Works | C | (26-40)%
Other: Placed Orders for goods/Instrument
Constructions: 60% Completed | D | (41-60)%
Other: Received Goods /Intruments as per the order
Constructions: 80% Completed | E | (61-80)%
Other: Received Goods /Intruments as per the order
Construntions: 99% Completed | F | (81-99)%
Other: Completed Lists of goods and beneficiaries
Constructions : 100% Completed | G | -100%
Other : Issued Goods & Instruments to Identified institutions , CBOs